## Sheet1
Sprint | Tasks | In Progress | Completed
Sprint 1: Wireframes and Diagrams | Database Design and Schema
UML Diagrams
Design in App Navigation Structure
Estimated Duration: 6-7 days | Designing Application Screen Wireframes
Sprint 2: Framework and Language Training | Studying Further on Node.js
Estimated Duration: 6-7 days | Leaning React and React Native Library
Sprint 3: Database Design, Model Creation and Navigation | Designing and Creating Database
Creating Folder Heirarchy
Create Models and Class Structures
Implement Basic Navigation Structure
Estimated Duration: 7 days | Test Navigation
Sprint 4: Creation of Home Screen and Boat Layout Screen | Create Home Screen
Create Layout Screen
Create Boat Layout Screen
Estimated Duration: 4-5 days | Test Layout Screen
Sprint 5: Implementation of Boat Layout and Creation of Boat Member Screen | Implement Boat Layout
Test Boat Layout
Create People Screen
Create Add Person Screen
Estimated Duration: 6-7 days | Test Person Screen
Sprint 6: Implementation and Creation of Ready Screen | Create Ready Screen
Implement Google Maps API
Implement Stop Watch
Implement Creating Graphs
Estimated Duration: 6-7 days | Test Ready Screen
Sprint 7: Creation and Implementation of Analytics Screen | Create Analytics Screen
Implement Viewing Graphs
Estimated Duration: 3-4 days | Test Analytics Screen