## Sheet1
ID | Task | Story | Story Points | Estimation(Days) | Priority
1 | Database Schema and Design | As an Exec I want to be able to create a record of all the team members on the team so we can manage team member information easier | 10 | 1 | 1
2 | UML Diagrams |  | 10 | 2 | 2
3 | Design in App Navigation structure |  | 15 | 2 | 3
4 | Designing application screen wireframes |  | 5 | 1 | 4
5 | Studying further on NodeJS |  | 15 | 3 | 5
6 | Learning React and React Native Library |  | 15 | 3 | 6
7 | designing and creating database |  | 10 | 2 | 7
8 | Creating folder hiearchy |  | 5 | 1 | 8
9 | create models and class structure |  | 15 | 2 | 9
10 | Implement basic navigation structure |  | 15 | 1 | 20
11 | Test navigation |  | 5 | 1 | 11
12 | Create home screen |  | 10 | 1 | 12
13 | create layout screen | As a Team Captain I want to be able to simulate a boat’s layout so I can more efficiently determine boat layouts for practices and competitions | 10 | 1 | 13
14 | Create boat layout page | As a Team Captain I want to be able to simulate a boat’s layout so I can more efficiently determine boat layouts for practices and competitions | 10 | 1 | 14
15 | test layout screen |  | 10 | 1 | 15
16 | implement boat layout | As a Team Captain I want to be able to manage multiple boat layouts so I can pick the best layout for certain situations instead of redoing the layout every time | 15 | 2 | 16
17 | test boat layout |  | 5 | 1 | 17
18 | create people screen | As an Exec I want to be able to create a record of all the team members on the team so we can manage team member information easier | 10 | 1 | 18
19 | create add person page | As an Exec I want to be able to create a record of all the team members on the team so we can manage team member information easier | 10 | 1 | 19
20 | test people screen | As an Exec I want to be able to create a record of all the team members on the team so we can manage team member information easier | 5 | 1 | 20
21 | create ready screen | As a Coach I want to be able to view the boat moving on a map so I can track our position on a boat during practice to help our performance | 10 | 1 | 21
22 | implement google maps api | As a Coach I want to be able to manage a record of performance graphs about each boat layout so I can monitor the teams progress and adjust my routine accordingly | 15 | 2 | 22
23 | implement stop watch | As a Coach I want to be able to record our boat’s distance travelled like a distance tracking stopwatch so I can analyze how long it takes us to travel a certain distance during practice | 5 | 1 | 23
24 | implement creating graphs |  | 15 | 1 | 24
25 | test ready screen |  | 5 | 1 | 25
26 | create analytics screen | As a Coach I want to be able to manage a record of performance graphs about each boat layout so I can monitor the teams progress and adjust my routine accordingly | 10 | 1 | 26
27 | implement viewing graphs | As a Coach I want to be able to view a graph of our speed against time on the boat after completing a set so I can analyze the strengths and weaknesses of our performance | 10 | 1 | 27
28 | test analytics screen | As a Coach I want to be able to manage a record of performance graphs about each boat layout so I can monitor the teams progress and adjust my routine accordingly | 5 | 1 | 28