# Project Status Report I

|  |
| --- |
| Date of Report Issue/Prepared: 07/01/2020 |

Report Prepared By: Andrew Cobb

Employer/Organization: Joey Corp

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | How to Train Your Dragon Boat | |
| T04 | |
| Start Date: **Jan 06, 2020** | End Date: **Jan 19, 2020** |
| Yellow | |

Summary

|  |
| --- |
| **Project Status Summary** |
| Group members where tasked with familiarizing themselves with React native framework as well as implicating basic navigation layout for application. Progress was made but not enough to realize all of our goals. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Training in React Native |  |
| Implicating basic navigation layout |  |

Upcoming Objectives for Jan 20, 2020 to Feb 2, 2020

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To | | Duration | Date |
| Implicating basic navigation layout | Arsalan Farooqui | | 3 Days | 13/01/2020 |
| Implement SQLite Database | Andrew Cobb | |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Create first React phone application with navigation and pages | | Arsalan Farooqui |  |
|  | |  |  |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Setting up react environment for all team member |  |  |
| Coordinating with new team member |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Project Members varying experience will cause discoordination | Low: Project Members have worked on multiple projects with proper coordination | Med | Communication will be established with all members to coordinate tasks that each member prefers |
| Project Schedule interfered by Education Schedule | High: All Project Members are active participants in education, weekly occurrence | Low | Project Timelines and Task Durations design with education as a factor, includes deadlines to be extended if necessary. |
| Absence of Project Member during meeting | Low: Communication with all members established outside meetings | Low | New Meetup date will be set to accommodate the member, or information from the current meeting will be relayed to the absent member. |
| Project Methodology foreign to project members | Medium: previous experience with other methodologies and requirements. | Med | Previous experience will be used as a tool for development throughout the project |

**NOTE: Attach additional sheets if insufficient space available**